## List1
Task description | Estimated hours | Work done (estimated hours, not real) | Comment
| 156 | 210
Siteadmin panel
Basic functionality
Login (form + processing) |  | 10
Menu + new design |  | 16
Locations
Grid |  | 8
Add/Edit form |  | 8
Background tasks |  | ? | will there be any background tasks, like creating a subdomain for location, etc.?
Advertisers
Grid |  | 6
Add/Edit form |  | 8
Categories
Grid with hierarchy |  | 24
Add/Edit form |  | 6
Listings
Grid |  | 6
Add/Edit form |  | 6
Add/Edit coupons form functionality |  | 16
Settings
Edit form | 4
Prices - I probably meant Plans
Grid |  | 6
Add/Edit form |  | 4
Premium ads
Grid |  | 6
Add/Edit form |  | 4
Autoresponsers
Edit form |  | 4
Sending autoresponsers | ? |  | how they work? when should they be sent?
Media Brokers
Grid | 6
Add/Edit form | ? |  | I'm not sure what is Media broker and what he does, is it affiliate?
Newsletter
Create newsletter form | 6
Send newsletter (background task) | 12
CSV Import
Import | ?
Frontend
Webpage
Main look |  | 24
Directory view |  | 10
Page (listing) |  | 16
Category view |  | 10
New, Ends soon, Favs views | 16
Tell a friend | 6
Display coupons |  | 4
Redeem coupons | 12
Display Premium ads |  | 8
Clicks tracking | 8
Advertisers
Register form | 8
Login form + login processing | 6
Forgot password form | 8
Edit account form | 4
View own listings | 4
Add/edit/delete listing form | 16
View statistics | 20 |  | it is not defined what kind of statistics will be available
Choose and pay for advertising plan | 20 |  | integration with payment processor. It could take more than estimated.