## List1
Task description | Estimated hours | Comment
366
Siteadmin panel
Basic functionality
Login (form + processing) | 10
Menu + new design | 16
Locations
Grid | 8
Add/Edit form | 8
Background tasks | ? | will there be any background tasks, like creating a subdomain for location, etc.?
Advertisers
Grid | 6
Add/Edit form | 8
Categories
Grid with hierarchy | 24
Add/Edit form | 6
Listings
Grid | 6
Add/Edit form | 6
Add/Edit coupons form functionality | 16
Settings
Edit form | 4
Prices
Grid | 6
Add/Edit form | 4
Premium ads
Grid | 6
Add/Edit form | 4
Autoresponsers
Edit form | 4
Sending autoresponsers | ? | how they work? when should they be sent?
Media Brokers
Grid | 6
Add/Edit form | ? | I'm not sure what is Media broker and what he does, is it affiliate?
Newsletter
Create newsletter form | 6
Send newsletter (background task) | 12
CSV Import
Import | ? | I'm not sure how import should work. What are Members?
Frontend
Webpage
Main look | 24
Directory view | 10
Page (listing) | 16
Category view | 10
New, Ends soon, Favs views | 16
Tell a friend | 6
Display + Redeem coupons | 16
Display Premium ads | 8
Clicks tracking | 8
Advertisers
Register form | 8
Login form + login processing | 6
Forgot password form | 8
Edit account form | 4
View own listings | 4
Add/edit/delete listing form | 16
View statistics | 20 | it is not defined what kind of statistics will be available
Choose and pay for advertising plan | 20 | integration with payment processor. It could take more than estimated.

## List2
Total time (hours) |  | 254
When | Who | Duration | Task
3.11.2011 | Maros | 2 | Generation of application skeleton
|  | 6 | Adding siteadmin module to the application
4.11.2011 | Maros | 8 | Work on siteadmin module - adding login and basic users management
5.11.2011 | Maros | 6 | Applying new design to siteadmin - basic window, most common controls
7.11.2011 | Maros | 2 | Grid + Add/edit form for Whitelist Account
|  | 2 | Grid + Add/edit form for Admins
|  | 4 | Distinguish superadmin & whitelist admin during login, ability to have different permissions and display different menu
8.11.2011 | Maros | 8 | Locations Grid + Add/Edit form
9.11.2011 | Maros | 10 | Categories Grid + Add/Edit form + hierarchical view of categories & sub-categories
10.11.2011 | Maros | 1 | added move up & down for categories
| Maros | 1 | added default whitelabel account switch
10.11.2011 | Tomas | 2 | Grid + Add/edit form for Advertisers
|  | 6 | Grid + Add/edit form for Listings
11.11.2011 | Maros | 6 | Frontend initial structure and new design
13.11.2011 | Maros | 6 | Displaying categories, subcategories, other locations, switching location
14.11.2011 | Maros | 2 | Displaying list of locations, location details and a map
14.11.2011 | Maros | 6 | Refactoring classes, added search to frontend, added images uypload to categories, listings and locations
15.11.2011 | Maros | 6 | Coupons added to Listings + Coupons added to frontend + Coupon detail
16.11.2011 | Maros | 8 | Plans management + Whitelabel Plans management
17.11.2011 | Tomas | 8 | Premium Ads management & displaying in the frontend - not finished
17.11.2011 | Maros | 3 | Plan types definition and saving
18.11.2011 | Tomas | 3 | Finished Premium Ads management
18.11.2011 | Maros | 4 | Started with Advertiers in frontend., changed the handling of advertisers in siteadmin
21.11.2011 | Maros | 4 | Advertisers signup, login, My account editation
23.11.2011 | Maros | 2 | Forgot password functionality + real email sending
23.11.2011 | Maros | 2 | Advertisers finished + info page in frontend
24.11.2011 | Maros | 4 | Improved form design in My account, Advertisers, Listings, Locations, Categories
25.11.2011 | Maros | 4 | Added My Plans and possibility to buy a plan (simulated)
25.11.2011 | Maros | 2 | Added check for correct plan and decrease plan limit when adding listing
25.11.2011 | Maros | 3 | Added Settings screen to whitelabel siteadmin, added missing fields toWhitelabel account
28.11.2011 | Maros | 3 | Customer registration, displaylast customers in the dashboard, New Offers, Ending soon
28.11.2011 | Maros | 6 | Implemented all plan limitations except Premium Ads per advertiser
29.11.2011 | Maros | 8 | Changed plans to support subscriptons and recurring payments, improved limitations checks for all limits. Started work on coupons redeeming
30.11.2011 | Maros | 4 | Customer and Employee table, continued work on redeeming
30.11.2011 | Maros | 4 | Started work on PayPal IPN handling for recurring payments for plans
1.12.2011 | Maros | 9 | view & change advertiser plans by white label admin, putpromocast to the final server, solve links problems, continued work on PayPal IPN
2.12.2011 | Maros | 7 | PayPal IPN integration
4.12.2011 | Maros | 4 | PayPal integration finished and coupons redemption proces finished
5.11.2011 | Maros | 8 | Authorize.net payments implemented
6.11.2011 | Maros | 2 | Recognize account and location by domain
6.11.2011 | Maros | 2 | Put order form to special HTTPS domain
6.11.2011 | Maros | 7 | Media broker signup & login, referral tracking (clicks) using cookies
7.11.2011 | Maros | 8 | Media broker referrals & commissions report for both media broker and whitelabel admin
8.11.2011 | Maros | 8 | promocode for affiliate random generation, started with reports data tracking, changedomain/subdomain to mandatory for locations & accounts
9.11.2011 | Maros | 3 | Finished data reports tracking, tested domains/subdomains recognition for account/location
12.11.2011 | Maros | 8 | Reports - quick stats data
13.11.2011 | Maros | 8 | Reports - added date from-to filter, started work on custom filter. Contact Form partially finished
14.11.2011 | Maros | 8 | fixing JavaScript errors and problems introduces by update to newest design
15.11.2011 | Maros | 8 | Reports - usage charts, Promos - data. Added White Label Purchased Plans
16.11.2011 | Maros | 8 | displaying after delete confirmation